## Sheet1
ALICE THORPE - GANTT CHART
Week
Task | Start | End | Complete | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Proposal | 1 | 2
Planning
Initial Ideas | 1 | 2 | ✔ | bar: Week 1 to Week 2
Subject Matter Research | 2 | 3 | ✔ | bar: Week 2 to Week 3
Further targetted research | 2 | 3 | ✔ | bar: Week 2 to Week 3
Audience Research | 2 | 3 | ✔ | bar: Week 2 to Week 3
Participant interview | 3 | 4 | ✔ | bar: Week 3 to Week 4
Analyse Examples | 3 | 5 | ✔ | bar: Week 3 to Week 5
Pitch Idea | 5 | 5 | ✔ | bar: Week 5
Budget
Draft budget | 4 | 6 | bar: Week 4 to Week 6
Development
Initial Ideas | 4 | 6 | ✔ | bar: Week 4 to Week 6
Logo Design & Development | 4 | 6 | ✔ | bar: Week 4 to Week 6
Realisation of UI | 5 | 7 | ✔ | bar: Week 5 to Week 7
Adobe XD Prototype | 5 | 7 | ✔ | bar: Week 5 to Week 7
Mockups | 8 | 10 | bar: Week 8 to Week 10
Advertisement Animation | 8 | 10 | bar: Week 8 to Week 10
Example Animation | 8 | 10 | bar: Week 8 to Week 10
Reflection
Test product | 9 | 11 | bar: Week 9 to Week 11
Feedback | 10 | 11 | bar: Week 10 to Week 11
Identify Improvements | 10 | 11 | bar: Week 10 to Week 11
Personal reflection 500 words | 11 | 12 | bar: Week 11 to Week 12
Critical Evaluation 500 words | 11 | 12 | bar: Week 11 to Week 12